## Week 2
MCI Project Weekly Time Sheet
Team | 24 | Student ID | a1798286 |  |  | Week starting: | 2
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday |  | 14:00 | 17:00 | 3 | Research similar applications and websites | To get ideas of project interface design | Discuss with group in the coming meeting
Tuesday |  | 14:00 | 15:00 | 1 | Client meeting | Update project progress | Fulfill client's requirement
Wednesday |  | 10:00 | 18:00 | 8 | Learn how to use UI design tool Figma | Visualizing the UI design | Complete 1/2 of the LinkedIn Figma course
Thursday |  | 9:00 | 17:00 | 8 | Learn Ionic and Angular JS | A tool for application development as required by client | Complete the first two sections of an Udemy Ionic course
Friday
Saturday
|  |  | Total | 20

## Week 3
MCI Project Weekly Time Sheet
Team | 24 | Student ID | a1798286 |  |  | Week starting: | 3
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday |  | 12:00 | 17:00 | 5 | Learn how to use UI design tool Figma | Visualizing the UI design | Complete another 1/2 of the LinkedIn Figma course
Tuesday |  | 10:00 | 17:00 | 7 | 1) Learn Ionic and Angular JS 2)Client meeting | 1) A tool for application development as required by client 2) update project progress | 1) Complete section 3 of the ionic course 2) fulfill client's requirement
Wednesday |  | 9:00 | 12:00 | 3 | Writing meeting minutes | For group record and reference | Push to github for review
Thursday |  | 9:00 | 15:00 | 6 | Finish first draft of pitch presentation | More time to prepare the pitch presentation | Discuss in the Friday internal meeting
Friday |  | 16:00 | 18:00 | 2 | Discuss the first draft of pitch slides | Rectify the pitch slides | Discuss in Tuesday client meeting
Saturday
|  |  | Total | 23

## Week 4
MCI Project Weekly Time Sheet
Team | 24 | Student ID | a1798286 |  |  | Week starting: | 4
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday
Tuesday |  | 9:00 | 17:00 | 8 | 1) Learn Ionic and Angular JS 2)Client meeting | 1) A tool for application development as required by client 2) update project progress | 1) Complete 1/2 of the ionic course section 4 2) fulfill client's requirement
Wednesday |  | 9:00 | 17:00 | 8 | Learn Ionic and Angular JS | A tool for application development as required by client | Complete another 1/2 of the ionic course section 4
Thursday
Friday |  | 16:00 | 20:00 | 4 | Record the presentation video | Pitch Presentation to client | Review with team mates
Saturday |  | 14:30 | 15:30 | 1 | Discuss the milestone and the coming meeting agenda | Project management | Next client meeting
|  |  | Total | 21

## Week 5
MCI Project Weekly Time Sheet
Team | 24 | Student ID | a1798286 |  |  | Week starting: | 5
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday |  | 9:00 | 16:00 | 7 | Learn Ionic and Angular JS | A tool for application development as required by client | Complete 1/3 of the ionic course section 5
Tuesday |  | 14:00 | 15:00 | 1 | Client meeting | Update project progress | Fulfill client's requirement
Wednesday |  | 10:00 | 18:00 | 8 | Learn Ionic and Angular JS | A tool for application development as required by client | Complete 2/3 of the ionic course section 5
Thursday |  | 18:00 | 22:00 | 4 | Writing Business Case | One of the important document of the project | Review with team mates
Friday
Saturday |  | 11:00 | 12:00 | 1 | Business Case review | One of the important document of the project | Final Submission
|  |  | Total | 21

## Week 6
MCI Project Weekly Time Sheet
Team | 24 | Student ID | a1798286 |  |  | Week starting: | 6
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday |  | 9:00 | 16:00 | 7 | Learn Ionic and Angular JS | A tool for application development as required by client | Complete 40% of the ionic course section 6
Tuesday |  | 14:00 | 15:00 | 1 | Client meeting | Update project progress | Fulfill client's requirement
Wednesday |  | 11:00 | 18:00 | 7 | Learn Ionic and Angular JS | A tool for application development as required by client | Complete 40% of the ionic course section 6
Thursday |  | 10:00 | 7:00 | 7 | Homepage emotion circles resize (CSS part) | A key page of the app | Review with team mates in the meeting on next Sat
Friday
Saturday
|  |  | Total | 22

## Mid-sem break week 1
MCI Project Weekly Time Sheet
Team | 24 | Student ID | a1798286 |  |  | Week starting: | 7
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday
Tuesday |  | 14:00 | 16:00 | 2 | Learn Ionic and Angular JS | A tool for application development as required by client | Complete another 20 % of the ionic course section 6
Wednesday
Thursday |  | 10:00 | 18:00 | 8 | Homepage emotion circles resize | A key page of the app | Review with team mates in the meeting on Sat
Friday |  | 11:00 | 19:00 | 8 | Homepage emotion circles resize(Angular JS part) | A key page of the app | Review with team mates in the meeting on Sat
Saturday |  | 13:00 | 18:00 | 5 | Group Meeting | Code review and docker & django demonstration | Development of Django database
|  |  | Total | 23

## Mid-sem break week 2
MCI Project Weekly Time Sheet
Team | 24 | Student ID | a1798286 |  |  | Week starting: | 7
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday |  | 9:00 | 10:00 | 1 | Prepare the meeting in the next day | Regular client meeting | Meeting will be held at 2:00 in the next day
Tuesday
Wednesday |  | 11:00 | 16:00 | 5 | Learn Ionic and Angular JS | A tool for application development as required by client | Complete another 15 % of the ionic course section 6
Thursday |  | 10:00 | 15:00 | 5 | Learn Ionic and Angular JS | A tool for application development as required by client | Complete another 10 % of the ionic course section 6
Friday |  | 11:00 | 17:00 | 6 | Learn Ionic and Angular JS | A tool for application development as required by client | Complete another 15 % of the ionic course section 6
Saturday |  | 14:00 | 15:00 | 1 | Ready for milestone 1 presentation to client | Complete milestone 1 | Milestone 2 plan
|  |  | Total | 18

## Week 7
MCI Project Weekly Time Sheet
Team | 24 | Student ID | a1798286 |  |  | Week starting: | 7
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday |  | 9:00 | 10:00 | 1 | Prepare the meeting in the next day | Regular client meeting | Meeting will be held at 2:00 in the next day
Tuesday |  | 14:00 | 15:00 | 1 | Client meeting | Feedback on milestone 1 | Provide additional resources to client
Wednesday |  | 10:00 | 16:00 | 6 | Learn Ionic and Angular JS | A tool for application development as required by client | Complete another 15 % of the ionic course section 7
Thursday |  | 10:00 | 15:00 | 5 | Learn Ionic and Angular JS | A tool for application development as required by client | Complete another 15 % of the ionic course section 7
Friday |  | 11:00 | 18:00 | 7 | Learn Ionic and Angular JS | A tool for application development as required by client | Complete another 20 % of the ionic course section 7
Saturday |  | 14:00 | 17:00 | 3 | Internal group meeting for milestone 2 issue | Start milestone 2 | Milestone 2 plan submission
|  |  | Total | 23

## Week 8
MCI Project Weekly Time Sheet
Team | 24 | Student ID | a1798286 |  |  | Week starting: | 7
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday |  | 12:00 | 13:00 | 1 | Prepare the meeting in the next day | Regular client meeting | Meeting will be held at 2:00 in the next day
Tuesday |  | 14:00 | 15:00 | 1 | Client meeting | Report progress of milestone 2 | Continue completing milestone 2
Wednesday |  | 11:00 | 16:00 | 5 | Learn Ionic and Angular JS | A tool for application development as required by client | Complete another 20 % of the ionic course section 7
Thursday |  | 10:00 | 15:00 | 5 | Learn Ionic and Angular JS | A tool for application development as required by client | Complete another 20 % of the ionic course section 7
Friday |  | 11:00 | 17:00 | 6 | Learn Ionic and Angular JS | A tool for application development as required by client | Complete another 10 % of the ionic course section 7
Saturday |  | 15:00 | 17:00 | 2 | Internal group meeting for milestone 2 issue | Complete milestone 2 | Milestone 2 execution
|  |  | Total | 20

## Week 9
MCI Project Weekly Time Sheet
Team | 24 | Student ID | a1798286 |  |  | Week starting: | 7
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday |  | 9:00 | 10:00 | 1 | Prepare the meeting in the next day | Regular client meeting | Meeting will be held at 2:00 in the next day
Tuesday |  | 14:00 | 15:00 | 1 | Client meeting | Report progress of milestone 2 | Continue completing milestone 2
Wednesday |  | 11:00 | 18:00 | 7 | Working on HTTP request to create reflection and store in database | Main function of "Insight" page | Continue to finish this http request
Thursday |  | 10:00 | 15:00 | 5 | Working on HTTP request to create reflection and store in database | Main function of "Insight" page | Http request for "Timeline" page
Friday |  | 11:00 | 17:00 | 6 | Learn Ionic and Angular JS | A tool for application development as required by client | Complete another 40 % of the ionic course section 8
Saturday |  | 15:00 | 18:00 | 3 | Working on HTTP request to retrieve data from database and show it in "Timeline" page | Main function of "Timeline" page | Http request for "Timeline" page
|  |  | Total | 23

## Week 10
MCI Project Weekly Time Sheet
Team | 24 | Student ID | a1798286 |  |  | Week starting: | 7
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday |  | 9:00 | 12:00 | 3 | Working on HTTP request to retrieve data from database and show it in "Timeline" page | Main function of "Timeline" page | Http request for "Timeline" page
Tuesday |  | 14:00 | 15:00
Wednesday |  | 9:00 | 16:00 | 7 | Testing plan | Testing plan for implementing testing | Writing testing code
Thursday |  | 10:00 | 18:00 | 8 | Testing code | Automatic testing | Update testing plan
Friday |  | 11:00 | 15:00 | 4 | Working on HTTP request to retrieve data from database and show it in "Timeline" page | Main function of "Timeline" page | Http request for "Timeline" page
|  |  | Total | 22

## Week 11
MCI Project Weekly Time Sheet
Team | 24 | Student ID | a1798286 |  |  | Week starting: | 7
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday |  | 9:00 | 10:00 | 1 | Prepare the meeting in the next day | Regular client meeting | Meeting will be held at 2:00 in the next day
Tuesday |  | 14:00 | 15:00 | 1 | Client meeting | Report progress of milestone 2 | Continue completing milestone 2
Wednesday |  | 11:00 | 18:00 | 7 | Code review | Code style and organization of the code | Poster
Thursday |  | 10:00 | 15:00 | 5 | Preparation work for final demo | Demo presentation | Demo presentation
Friday |  | 17:00 | 23:00 | 6 | Poster | Poster as a summary of project | Poster review on the coming Sat
Saturday |  | 16:00 | 17:00 | 1 | Internal group meeting for poster issue | Poster as a summary of project | Poster submission
|  |  | Total | 21