## Week2
MCI Project Weekly Time Sheet
Team | 24 | Student ID | 1784870 |  |  | Week starting: | 2
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2021-03-08 | 10:00 | 13:00 | 3 | Learn and set up UX/UI tool Figma | Use Figma as a tool for application design | Start a figma dessign and set up shared file with teammates.
Tuesday | 2021-03-09 | 17:00 | 18:00 | 1 | Group Meeting | Discuss on prototy design within team | Set up github project backlog and make plans; Discuss major functionality and design
Wednesday | 2021-03-10 | 10:00 | 13:00 | 3 | Study project backgroud and Prepare Pitch Slide (Template & outline) | Prepare for Pitch Presentation | Understand EQ and the purpose of the application; Prepare a template and pitch outline structure; Set up as a shared document to teammates
Thursday | 2021-03-11 | 14:00 | 17:00 | 3 | Learn the Ionic Framework with Angular for mobile app development | Learn the skill stacks and tools for cross platform development | Learn why choose this framework; Get fimiliar with Ionic and Angular; Set up enviroment and get started
Friday | 2021-03-12 | 10:00 | 13:00 | 3 | Research on related iOS and Andriod apps Design Figma Prototype v0.5 | Design this prototype for week 3 client meeting discussion and Pitch presentation | Finish Figma Prototype v0.5 and get ready to discuss with teammates
|  | 16:00 | 18:00 | 2 | Weekly Group discussion | Prepare for week 3 client meeting and pitch presentation | Discuss Figma Prototype v0.5 and changes. Finish Agenda
|  | 18:00 | 21:00 | 3 | Figma Prototype v0.8 | Use this prototype for week 3 client meeting discussion and Pitch presentation | Finish Figma Prototype v0.8
Saturday | 2021-03-13 | 13:00 | 15:00 | 3 | Learn the Ionic Framework with Angular for mobile app development |  | Complete 10% of the online course at Udemy
|  |  | Total | 21

## Week3
MCI Project Weekly Time Sheet
Team | 24 | Student ID | 1784870 |  |  | Week starting: | 3
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2021-03-15 | 10:00 | 12:00 | 2 | Learn Ionic on Udemy | Use Ionic framework for application development | Learn basic Ionic component and documents. Build a demo with vanilla JavaScript
Tuesday | 2021-03-16 | 14:00 | 14:30 | 0.5 | Client Meeting | Discuss on prototy design within team | Set up github project backlog and make plans; Discuss major functionality and design
|  | 14:30 | 16:30 | 2 | Team Meeting | Plan and set goals | Discuss clients requirments and how to make changes on Product Design. Plan for Pitch presentation; Set weekly tasks;
|  | 18:00 | 20:00 | 2 | Modify Figma Prototype v1.2 | Reflect clients' feedback on functionalities and logic | Redesign on functionalities, single emotion pages, add signup and login pages, permission pages; Add tabs, redesign logical flow between pages
Wednesday | 2021-03-17 | 10:00 | 0:00 | 2 | Prepare Pitch Slide (What) | Prepare for Pitch Presentation | Prepare a template and pitch outline structure; Set up as a shared document to teammates
Thursday | 2021-03-18 | 14:00 | 17:00 | 3 | Learn Ionic + Angular on Udemy | Use Ionic + Angular for application development | Watch tutorial on Udemy; start build demo with Ionic and pure JS
Friday | 2021-03-19 | 16:00 | 18:00 | 2 | Weekly Group discussion on Pitch slides and Prototype v1.2; Introduce management tool Slack | Prepare for week 4 client meeting and pitch presentation slide draft | Finish next week Agenda; Discussion on modify Pitch slides content and present style; Set up Slack
|  | 18:00 | 20:00 | 2 | Figma Prototype v1.5 | Use this prototype for week 4 client meeting discussion | Modified Insights page content and routing logical;Finish Figma Prototype v1.2
Saturday | 2021-03-20 | 13:00 | 15:00 | 2 | Prepare Pitch Slide (What part) | Midify what part | Ready for discussion on next client meeting
Sunday | 2021-03-21 | 13:00 | 16:00 | 3 | Learn Ionic + Angular on Udemy | Use Ionic + Angular for application development | Complete 10% of the online course at Udemy
|  |  | Total | 20.5

## Week4
MCI Project Weekly Time Sheet
Team | 24 | Student ID | 1784870 |  |  | Week starting: | 4
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2021-03-22 | 12:00 | 14:00 | 2 | Prepare Pitch Slide (What) | Prepare for Pitch Presentation | Finish what part
Tuesday | 2021-03-23 | 14:00 | 14:30 | 0.5 | Client Meeting | Discuss on prototy design and Pitch | Get feedback for app prototype design and pitch slides
|  | 14:30 | 15:30 | 1 | Team Meeting | Work on Pitch, milestones | Plan for Pitch presentation; Set weekly tasks;
|  | 16:00 | 17:00 | 1 | Modify Figma Prototype v2 | Reflect clients' feedback on functionalities and logic | add strategy function to provide articles
Wednesday | 2021-03-24 | 10:00 | 0:00 | 2 | Prepare Pitch Slide (What) | Prepare for Pitch Presentation | Finish final slide and get feedback from tutor and instructor; practise on presentation
Thursday | 2021-03-25 | 14:00 | 17:00 | 3 | Learn Angular | UseAngular for application development | Learn Angular document and write demo app
Friday | 2021-03-26 | 16:00 | 18:00 | 2 | Write business case and milestone plan | Help plan, organise and track project development process | Introduce to teammates; Set up WorkPlace and channels for team; Organise resources on channels.
|  | 17:00 | 20:00 | 3 | Learn Ionic + Angular on Udemy | Use Ionic + Angular for application development | Watch tutorial on Udemy; start build demo with Ionic and angular
Saturday | 2021-03-27 | 14:00 | 16:00 | 2 | Group meeting | Work on Pitch, milestones | Ready for discussion on next client meeting
|  | 16:00 | 17:00 | 1 | Write business case and milstone | Midify what part | Ready for discussion on next client meeting
Sunday | 2021-03-28 | 14:00 | 19:00 | 5 | Pitch Video | Take video for presentation | Finish presentatio video
|  |  | Total | 22.5

## Week5
MCI Project Weekly Time Sheet
Team | 24 | Student ID | 1784870 |  |  | Week starting: | 5
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2021-03-29 | 12:00 | 14:00 | 2 | Write business case and milestone plan | Help plan, organise and track project development process | Finish what part and milestone draft
Tuesday | 2021-03-30 | 15:00 | 18:00 | 3 | Team Meeting | Start on mailstone 1 development | Learn Angular + Ionic, finish basic routing and start hpme page
Wednesday | 2021-03-31 | 13:00 | 17:00 | 4 | Developing Landing and login | Develop functionalities | Finish landing page and login signup front end basic look
Thursday | 2021-04-01 | 15:00 | 17:00 | 2 | Team meeting - Write business case and milestone plan | Help plan, organise and track project development process | Go over the milestone plan and bcase draft and make adjustment
Friday | 2021-04-02 | 16:00 | 18:00 | 2 | Write business case and milestone plan | Help plan, organise and track project development process | Adjust mileston based on clients' feedback
|  | 14:00 | 17:00 | 3 | Working on login / signup | Develop functionalities | Finish login/signup page using segement and router
Saturday | 2021-04-03 | 14:00 | 17:00 | 3 | Working on alert component | Develop functionalities | Finish alert page for access permission
|  | 16:00 | 5:00 | 1 | Agenda & Timesheet | For clients meeting | Ready for discussion on next client meeting
Sunday | 2021-04-04 | 20:00 | 20:30 | 0.5 | Write business case and milestone plan | Bcase and milstone doc | Final adjustment for submission
|  |  | Total | 20.5

## Week6
MCI Project Weekly Time Sheet
Team | 24 | Student ID | 1784870 |  |  | Week starting: | 6
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2021-04-05 | 13:00 | 16:00 | 3 | Work on routing and first demo | Develop auth functionalities | Working on first demo
Tuesday | 2021-04-06 | 15:00 | 18:00 | 3 | Team Meeting | Start on mailstone 1 development | Learn Angular + Ionic, finish basic routing and start hpme page
Wednesday | 2021-04-07 | 13:00 | 16:00 | 3 | Study Firebase and auth | Develop functionalities | Work on login signup front end basic look
Thursday | 2021-04-08 | 14:00 | 16:00 | 2 | Work on auth with firebae | Develop functionalities | Work on login signup front end basic look
Friday | 2021-04-09 | 16:00 | 17:00 | 1 | Team Meeting | Help plan, organise and track project development process | Adjust mileston based on clients' feedback
Saturday | 2021-04-11 | 14:00 | 17:00 | 3 | Working on alert component | Develop functionalities | Finish alert page for access permission
Sunday | 2021-04-12 | 13:00 | 18:00 | 5 | Working on Google Auth | Develop functionalities | Finish login/signup page using segement and router
|  |  | Total | 20

## Midbreak
MCI Project Weekly Time Sheet
Team | 24 | Student ID | 1784870 |  |  | Week starting: | MidBreak
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2021-04-13
Tuesday | 2021-04-14
Wednesday | 2021-04-15 | 14:00 | 22:00 | 6 | Firebase and Promise | Develop functionalities | Working on google auth and email register
Thursday | 2021-04-16 | 15:00 | 16:00 | 3 | Team meeting - Write business case and milestone plan | Help plan, organise and track project development process | Go over the milestone plan and bcase draft and make adjustment
Friday | 2021-04-17 | 16:00 | 17:00 | 3 | Develop Dashboard | Help plan, organise and track project development process | Working on Dashboard with user data
Saturday | 2021-04-18 | 14:00 | 17:00 | 3 | Team Meeting | Discuss developing progress | Learn Django and Firebase
Sunday | 2021-04-19 | 14:00 | 17:00 | 3 | Working on Google Auth | Develop functionalities | Finish alert page for access permission
Monday | 2021-04-20
Tuesday | 2021-04-21
Wednesday | 2021-04-22
Thursday | 2021-04-23 | 14:00 | 17:00 | 3 | Team Meeting | Prepare for milestone 1
Friday | 2021-04-24
Saturday | 2021-04-25
Sunday | 2021-04-26 | 16:00 | 4:30 | 1 | Agenda & Timesheet | For clients meeting | Ready for discussion on next client meeting
|  |  | Total | 22