## week 4
MCI Project Weekly Time Sheet
Team | 24 | Student ID | a1792395 |  |  | Week starting: | 4
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2021-03-22 | 20:00 | 21:00 | 1 | Learn the Ionic Framework with Angular for mobile app development | Learn the framwork and language for developing our App | Continue to watch Ionic tutorial video on Youtube
Tuesday | 2021-03-23 | 14:00 | 14:30 | 0.5 | Meeting with client in Zoom | Discuss the protype design and pitch presentation | We adjusted the pitch slide and remove the parts that clients consider as not important
Tuesday | 2021-03-23 | 14:30 | 15:30 | 1 | Group internal meeting in Zoom | weekly planing for the project | prepare for pitch presentation, discussed and adjust the slide to satisfied clients' requirements
Wednesday | 2021-03-24 | 21:00 | 22:00 | 1 | Prepare the minutes on week 4 client meeting | A wrap up of clients meeting | summarize the ideas and comments from clients
Friday | 2021-03-26 | 19:00 | 23:00 | 4 | Modify the pitch slide | prepare for pitch presentation | Modify the feasibility part, mostly focus on milestone, cooperation with client's lab, and techlonogy stack
Saturday | 2021-03-27 | 14:45 | 16:00 | 1.25 | Group internal meeting in Zoom | Prepare for week 5 client meeting, business case, milestone and pitch presentation | Prepare for week 5 agenda, work on business case and milestone
|  |  | Total | 8.75

## week 3
MCI Project Weekly Time Sheet
Team | 24 | Student ID | a1792395 |  |  | Week starting: | 3
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2021-03-15 | 21:00 | 23:00 | 2 | Learn the Ionic Framework with Angular for mobile app development | Learn the framwork and language for developing our App | Continue to watch Ionic tutorial video on Youtube
Tuesday | 2021-03-16 | 14:00 | 14:30 | 0.5 | Meeting with client in Zoom | Discuss the protype design and prioritise major features | To change the prototype design as per clients request, including the layout of explore page and home page
Tuesday | 2021-03-16 | 14:30 | 15:30 | 2 | Group internal meeting in Zoom | weekly planing for the project | prepare for pitch presentation, discussed and adjust the prototype to satisfied clients' requirements
Wednesday | 2021-03-17 | 20:00 | 22:00 | 0 | Adjust the pitch slide | prepare for pitch presentation | Changed the content of pitch slide as per internal group discussion
Thursday | 2021-03-18 | 20:00 | 22:00 | 2 | Learn the Ionic Framework with Angular for mobile app development | Learn the framwork and language for developing our App | Continue to watch Ionic tutorial video on Youtube
Friday | 2021-03-19 | 16:00 | 17:00 | 1 | Group internal meeting in Zoom | Prepare for week 4 client meeting and pitch presentation | Prepare for week 4 agenda, adjust pitch slide
Sunday | 2021-03-21 | 20:00 | 22:00 | 2 | Learn the Ionic Framework with Angular for mobile app development | Learn the framwork and language for developing our App | Continue to watch Ionic tutorial video on Youtube
|  |  | Total | 9.5

## week 2
MCI Project Weekly Time Sheet
Team | 24 | Student ID | a1792395 |  |  | Week starting: | 2
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2021-03-08 | 20:00 | 22:00 | 2 | Learning React Native | We decided to use React Native as devloping language | Enrolled and started in a online course in edX about mobile app development in React Native
Tuesday | 2021-03-09 | 17:00 | 18:00 | 1 | Group internal meeting in person | Discuss the interface and resources | We discussed about the major functionality and interface layout and decided to use Figma for interface design; shared online resources of learning React Native; I found out that I have not been added to the GitHub team repository so I decided to send an email to lecturer about it
Wednesday | 2021-03-10 | 20:00 | 22:00 | 2 | Making demo interface elements in Photoshop | To statisfiy our clients' preference on using bubble chart to illustrate the emotions in the interface | 5 emomtions bubble with transaprenet in png format
Thursday | 2021-03-11 | 16:00 | 17:00 | 1 | Group internal meeting in Zoom | Prepare for week 3 client meeting and pitch presentation | Discuss the meeting agenda, interface orototype v0.5 and amended changes, set internal deadlines of pitch presentation slide to 19 March
|  | 20:00 | 22:00 | 2 | Learn the Ionic Framework with Angular for mobile app development | Our clients require us to use Ionic instead of React Native to develop the App | Started to watch Ionic tutorial video on Youtube
Friday | 2021-03-12 | 20:00 | 22:00 | 2 | Research on existing App in market | We need to compare our product to existing App in market to find out why is our product better than others | Adopted design some ideas from existing App, but also found out the differences between our product and existing solution
Saturday | 2021-03-13 | 15:00 | 17:00 | 2 | Learn the Ionic Framework with Angular for mobile app development | Learn the framwork and language for developing our App | Continue to watch Ionic tutorial video on Youtube
|  |  | Total | 12