## Yingyao Lu
MCI Project Weekly Time Sheet
Team | 24 | Student ID | 1784870 |  |  | Week starting: | 3
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2021-03-15 | 10:00 | 12:00 | 2 | Learn Ionic on Udemy | Use Ionic framework for application development | Learn basic Ionic component and documents. Build a demo with vanilla JavaScript
Tuesday | 2021-03-16 | 14:00 | 14:30 | 0.5 | Client Meeting | Discuss on prototy design within team | Set up github project backlog and make plans; Discuss major functionality and design
|  | 14:30 | 15:30 | 1 | Team Meeting | Plan and set goals | Discuss clients requirments and how to make changes on Product Design. Plan for Pitch presentation; Set weekly tasks;
|  | 18:00 | 20:00 | 2 | Modify Figma Prototype v1.2 | Reflect clients' feedback on functionalities and logic | Redesign on functionalities, single emotion pages, add signup and login pages, permission pages; Add tabs, redesign logical flow between pages
Wednesday | 2021-03-17 | 10:00 | 0:00 | 2 | Prepare Pitch Slide (What) | Prepare for Pitch Presentation | Prepare a template and pitch outline structure; Set up as a shared document to teammates
Thursday | 2021-03-18 | 14:00 | 17:00 | 3 | Learn Ionic + Angular on Udemy | Use Ionic + Angular for application development | Watch tutorial on Udemy; start build demo with Ionic and pure JS
Friday | 2021-03-19 | 16:00 | 17:00 | 1 | Weekly Group discussion on Pitch slides and Prototype v1.2 | Prepare for week 4 client meeting and pitch presentation slide draft | Finish next week Agenda; Discussion on how to modify Pitch slides content and present style; Agree on current design Figma Prototype v1.5
|  | 17:00 | 18:00 | 1 | Introduce management tool Slack | Help plan, organise and track project development process | Introduce to teammates; Set up WorkPlace and channels for team; Organise resources on channels.
|  | 18:00 | 19:00 | 1 | Figma Prototype v1.5 | Use this prototype for week 4 client meeting discussion | Modified Insights page content and routing logical;Finish Figma Prototype v1.2
Saturday | 2021-03-20 | 13:00 | 15:00 | 2 | Prepare Pitch Slide (What part) | Midify what part | Ready for discussion on next client meeting
Sunday | 2021-03-21 | 13:00 | 16:00 | 3 | Learn Ionic + Angular on Udemy | Use Ionic + Angular for application development | Complete 10% of the online course at Udemy
|  |  | Total | 18.5